## Summary
TCS
Overall Issues - Total Items |  | Overall Open/Reopen Issues By Priority |  | Open/Reopen Issues Today
Open | 35 | Blocker |  | No of Issues Open Today
Reopened |  | Critical |  | No of Issues Reopen Today
Closed | 200 | Major | 32 | No of Issues Closed Today
Resolved |  | Minor | 3
In-Progress |  | Trivial
Total | 235 | Total | 35
Last Updated Date |  | Last Update Time

## Bug Sheet
TCS
Type | Project Name | Roles/ Modules | BUG/TASK ID | Sprint | Summary | Reporter | Priority | Assigned to | Status | Date | QA Comments | DEV Comments
BUG | TCS - CENTRA | TEXTILE | CENTRA_001 |  | Supplier Creation - In the supplier details, the name field accepts the null value Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Without entering the data in name field Expected Result: It should allow the null value in the name field Reference: | BALAJI N | Major |  | Open | 19-09-2023
BUG | TCS - CENTRA | TEXTILE | CENTRA_002 |  | Supplier Creation - In the supplier details, the name field allow to enter the numeric value Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Enter the numeric data name field Expected Result: It should allow the numeric value in the name field Reference: | BALAJI N | Major |  | Open | 19-09-2023
BUG | TCS - CENTRA | TEXTILE | CENTRA_003 |  | Supplier Creation - In the supplier details, the name field allow to enter the special character value Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Enter the special character data name field Expected Result: It should allow the special character value in the name field Reference: | BALAJI N | Major |  | Open | 19-09-2023
BUG | TCS - CENTRA | TEXTILE | CENTRA_004 |  | Supplier Creation - In the address fields, it accept null value in first character Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Give the first character as null in the address field Expected Result: It should not allow to give first character as null Reference: | BALAJI N | Major |  | Open | 19-09-2023
BUG | TCS - CENTRA | TEXTILE | CENTRA_005 |  | Supplier Creation - In the city name fields, it display the mandatory * symbol with blank space on the city name label Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Observe the UI on the city name label Expected Result: It should be combined with city name* Reference: | BALAJI N | Minor |  | Open | 19-09-2023
BUG | TCS - CENTRA | TEXTILE | CENTRA_006 |  | Supplier Creation - In the pincode fields, it accepts the alphabetic characters Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Enter the alphabetic characters in pin code field Expected Result: It should not accept the alphabetic characters Reference: | BALAJI N | Major |  | Open | 19-09-2023
|  |  | CENTRA_007 |  | Supplier Creation - In the pincode fields, it accepts the special characters Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Enter the special characters in pin code field Expected Result: It should not accept the special characters Reference: | BALAJI N | Major |  | Open | 19-09-2023
|  |  | CENTRA_008 |  | Supplier Creation - In the phone1 & 2 fields, it accepts the special characters Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Enter the special characters in phone 1 & 2 field Expected Result: It should not accept the special characters Reference: |  | Major |  | Open
|  |  | CENTRA_009 |  | Supplier Creation - In the phone 2 fields, it displayed phone attached with serial number 2 in the UI of phone 2 label Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Observe the UI on phone 2 field Expected Result: It should display with space like Phone 2 Reference: |  | Minor |  | Open
|  |  | CENTRA_010 |  | Supplier Creation - In the mobile number field, mandatory symbol is not present Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Observe the UI on mobile number field Expected Result: It should display with mandatory symbol on the mobile number field Reference: |  | Minor |  | Open
|  |  | CENTRA_011 |  | Supplier Creation - In the mobile number field, accepts to enter the special and alphabetic characters Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Enter the alphabetic and special characters on mobile number field Expected Result: It should not allow to enter the alphabetic and special characters on the mobile number field Reference: |  | Major |  | Open
|  |  | CENTRA_012 |  | Supplier Creation - In the contact person field, accepts to enter the special and numeric characters Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Enter the numeric and special characters on mobile number field Expected Result: It should not allow to enter the numeric and special characters on the mobile number field Reference: |  | Major |  | Open
|  |  | CENTRA_013 |  | Supplier Creation - In the MSME ID field, allows to enter the more than 12 digits Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Enter the MSME ID more than 12 digits in MSME ID field Expected Result: It should not allow to enter more than 12 digits in MSME ID field Reference: |  | Major |  | Open
|  |  | CENTRA_014 |  | Supplier Creation - In the email id field, allows to enter the without .dot character Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Enter the Email ID without .dot character in the email id field Expected Result: It should not allow to enter with the .dot character in the email id field Reference: |  | Major |  | Open
|  |  | CENTRA_015 |  | Supplier Creation - In the email id field, allows to null character which is a mandatoty field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Give the null value on the email id field Expected Result: It should not allow to give the null character which is a mandatory field in the email id field Reference: |  | Major |  | Open
|  |  | CENTRA_016 |  | Supplier Creation - When user clicks the Order follow up field and then clicks anyother fields it navigate to the next A/c details page Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Press Ctrl+ N to create new supplier 6. Enter the email id in Order follow ups field 7. Click the Order follow ups field 8. Click anyother fields and observe the UI Expected Result: It should not allow navigate to the A/c details page Reference: |  | Major |  | Open
|  |  | CENTRA_017 |  | Supplier Creation - In the A/C details, it accepts to enter the numeric and special characters in the bank name field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the Bank Name Expected Result: It should not allow to enter the numeric and special characters in the bank name field Reference: |  | Major |  | Open
|  |  | CENTRA_018 |  | Supplier Creation - In the A/C details, it accepts to enter the more than 18 digits characters in the Account number field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the account number more than 18 digits in that field Expected Result: It should not allow to enter the more than 18 digits characters in the account number field Reference: |  | Major |  | Open
|  |  | CENTRA_019 |  | Supplier Creation - In the A/C details, it accepts to enter the alphabetic and special characters in the Account number field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the account number alphabetic and special characters in that field Expected Result: It should not allow to enter the alphabetic and special characters in the account number field Reference: |  | Major |  | Open
|  |  | CENTRA_020 |  | Supplier Creation - In the A/C details, it accepts to enter 1st characters as null value in the Bank city field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Give the null value in 1st characters in bank city field Expected Result: It should not allow to enter the null value in the bank city field Reference: |  | Major |  | Open
|  |  | CENTRA_021 |  | Supplier Creation - In the A/C details, it accepts to enter the numeric and special characters in the favour name field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the numeric and special characters in favour name field Expected Result: It should not allow to enter the numeric and special characters in the favour name field Reference: |  | Major |  | Open
|  |  | CENTRA_022 |  | Supplier Creation - In the A/C details, it accepts to enter the more than 10 characters in the PAN No field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the more than 10 digits in PAN No field Expected Result: It should not allow to enter the more than 10 digits in the PAN No field Reference: |  | Major |  | Open
|  |  | CENTRA_023 |  | Supplier Creation - In the A/C details, it accepts to enter special characters in the PAN No field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the special characters in PAN No field Expected Result: It should not allow to enter the special character in the PAN No field Reference: |  | Major |  | Open
|  |  | CENTRA_024 |  | Supplier Creation - In the A/C details, it accepts to enter the more than 11 characters in the CST No field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the more than 11 digits in CST No field Expected Result: It should not allow to enter the more than 11 digits in the CST No field Reference: |  | Major |  | Open
|  |  | CENTRA_025 |  | Supplier Creation - In the A/C details, it accepts to enter the special characters in the CST No field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the special characters in CST No field Expected Result: It should not allow to enter the special characters in the CST No field Reference: |  | Major |  | Open
|  |  | CENTRA_026 |  | Supplier Creation - In the A/C details, it accepts to enter the more than 15 characters in the LST No field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the more than 15 digits in LST No field Expected Result: It should not allow to enter the more than 11 digits in the LST No field Reference: |  | Major |  | Open
|  |  | CENTRA_027 |  | Supplier Creation - In the A/C details, it accepts to enter the special characters in the LST No field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the special characters in LST No field Expected Result: It should not allow to enter the special characters in the LST No field Reference: |  | Major |  | Open
|  |  | CENTRA_028 |  | Supplier Creation - In the A/C details, it accepts to enter the more than 11 characters in the Tin No field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the more than 11 digits in Tin No field Expected Result: It should not allow to enter the more than 11 digits in the Tin No field Reference: |  | Major |  | Open
|  |  | CENTRA_029 |  | Supplier Creation - In the A/C details, it accepts to enter the special characters in the Tin No field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the special characters in Tin No field Expected Result: It should not allow to enter the special characters in the Tin No field Reference: |  | Major |  | Open
|  |  | CENTRA_030 |  | Supplier Creation - In the A/C details, it accepts to enter the more than 11 characters in the ECC No field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the more than 11 digits in ECC No field Expected Result: It should not allow to enter the more than 11 digits in the ECC No field Reference: |  | Major |  | Open
|  |  | CENTRA_031 |  | Supplier Creation - In the A/C details, it accepts to enter the special characters in the ECC No field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the special characters in ECC No field Expected Result: It should not allow to enter the special characters in the ECC No field Reference: |  | Major |  | Open
|  |  | CENTRA_032 |  | Supplier Creation - In the A/C details, it accepts to enter the alphabetics & special characters in the regualr discount field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the alphabetics & special characters in regular discount field Expected Result: It should not allow to enter the alphabetics & special characters in the regular discount field Reference: |  | Major |  | Open
|  |  | CENTRA_033 |  | Supplier Creation - In the A/C details, it accepts to enter the alphabetics & special characters in the special discount field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the alphabetics & special characters in special discount field Expected Result: It should not allow to enter the alphabetics & special characters in the special discount field Reference: |  | Major |  | Open
|  |  | CENTRA_034 |  | Supplier Creation - In the A/C details, it accepts to enter the alphabetics & special characters in the less discount field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the alphabetics & special characters in less discount field Expected Result: It should not allow to enter the alphabetics & special characters in the less discount field Reference: |  | Major |  | Open
|  |  | CENTRA_035 |  | Supplier Creation - In the A/C details, it accepts to enter the 15 characters in the GST details ARN No field Steps to reproduce: 1. Login to the application 2. Go to masters in menu bar 3. Click the centra master 4. Click the supplier 5. Click the A/C details tab 6. Enter the more than 23 digits in GST details ARN No field Expected Result: It should allow to enter the 23 digits in the GST details ARN No field Reference: |  | Major |  | Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open
Open

## Test Cycle
Testing Cycle
Functional | Start Date | End Date | Available time
Test Execution
Functional Test on, module(Cycle 1)
Development team () Day
Retest & Regression
Functional Test on, Module (Cycle 2)
Development team () Day
Retest & Regression
Sanity ( Before Release)
User Acceptance Testing (Testing on Production)