## QA Estimation sheet
QA Test Estimation
QA Activities | Effort (Man hours) | Comments/Remarks
Test case design Phase
Existing application familiarization /Process flow/Knowledge for the team | 10
Requirement Analysis | 5
Test Plan / Test Strategy | 5
Test Environment setup | 10
Ad-hoc testing / Exploratory Testing | 10
Test case development including Peer review and updates | 30
Test lead/Coordination/status reporting efforts | 7 | Industry standard 10%
Total Design Efforts | 77
Test Execution Summary
Test execution (Cycle 1) | 40
Defect logging (Cycle 1) | 1
Test execution (Cycle 2) | 40
Defect logging (Cycle 2) | 8
Final defect round to meet exit criteria | 81 | Assumed 3 days approx for defect testing by 3 resources. Any pending open defects based on exit critieria and stability of the product
Sub total Execution effort | 170
Test lead/coordination effort | 17 | Industry standard 10%
Total Execution Efforts | 187
UAT | 40
UAT Support | 10 | Interacting with End Users and supporting.
Contingency factor 25% | 66 | since its highlevel and not full scope known on scenarios etc, Hence considered 25% as per TCOE process
Post Production support | 100
Training to support team | 30
Total Efforts (hours) | 510
Total Efforts in Man days | 63.75 | Assumed 9 hours/ day but actual productivity on testing excluding status calls, meetings, discussions, etc considered 8 hours/day
Other Parameters to be considered:
Show stopper defects with temporary fix using which continuation of test execution and the same need to be re-tested when it arrives in the build.
Any Showstopper bugs need to be addressed immediately to the development team by simulating in front of the development team
Performing a smoke test for that feature once the next QC build arrives to ensure no critical bugs because of code change
At times, development team may need QC team to simulate the bug as it may not arise in development environment which needs additional effort

## Sheet2
Provide your comments as:
1. How may test cases anticipated, data setup efforts if there are, complexities of test cases in numbers
2. Be ready for requirements traceability matrix which talks of test scenarios with complexities as shown in Sample Estimation details worksheet
For Example:
Total test cases anticipated:
Total simple test cases;
Total Medium Test cases:
Total High test cases:
Total Complex test cases:
Total Exceptional test cases: